## Work Plan
|  |  | 01.10.2020-07.10.2020 | 08.10.2020-14.10.2020 | 15.10.2020-21.10.2020 | 22.10.2020-28.10.2020 | 29.10.2020- 04.11.2020 | 05.11.2020- 11.11.2020 | 12.11.2020- 18.11.2020 | 19.11.2020- 25.11.2020 | 26.11.2020- 02.12.2020 | 03.12.2020- 09.12.2020 | 10.12.2020-16.12.2020 | 17.12.2020- 23.12.2020 | 24.01.2020-30.12.2020 | 31.12.2020 -06.12.2021
Start Date: 19/10/2020 | ASSIGNEE(s) |  | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14
Literature Review and Planning |  | Week (1-3) | bar: WEEK 1
Project Proposal and Revision | Beyza Yüksel, Eda Gül Sümer, Burcu Biter | bar: WEEK 1
Literature Review | Beyza Yüksel, Eda Gül Sümer, Burcu Biter | bar: WEEK 2 to WEEK 3
Preparing Work Load Plan | Beyza Yüksel, Eda Gül Sümer, Burcu Biter | bar: WEEK 3
Software Requirements Specification |  | Week (4-8) | bar: WEEK 4; WEEK 8
SRS Preparation | Beyza Yüksel, Eda Gül Sümer, Burcu Biter | bar: WEEK 4 to WEEK 8
Web Page Requirements | Beyza Yüksel, Eda Gül Sümer, Burcu Biter | bar: WEEK 4 to WEEK 8
Software Design Description |  | Week (8-11) | bar: WEEK 8
SDD Preparation | Beyza Yüksel, Eda Gül Sümer, Burcu Biter | bar: WEEK 8 to WEEK 11
Preparing Mid-Semester Presentation | Beyza Yüksel, Eda Gül Sümer, Burcu Biter | bar: WEEK 11
Project Website Update | Beyza Yüksel, Eda Gül Sümer, Burcu Biter | bar: WEEK 11
Project Report |  | Week (12-14) | bar: WEEK 12 to WEEK 14
Project Report and Presentation | Beyza Yüksel, Eda Gül Sümer, Burcu Biter | bar: WEEK 12 to WEEK 14